## Blad1
Project week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Calendar week | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Activity | [11 empty] | E
Pilot scale preparatory programming | [11 empty] | A
Project planning | [11 empty] | S
T
MS1: Planning report |  |  | • | [8 empty] | E
R
MS2: Half time evaluation | [8 empty] | • |  |  | -
Writing thesis | [11 empty] | V
MS3: Final draft | [11 empty] | A | [8 empty] | •
Preparing opposition
Preparing presentation | [11 empty] | C
MS4: Project presentation | [11 empty] | A | [9 empty] | •
Thesis corrections | [11 empty] | Y
MS5: Thesis ready | [11 empty] | ! | [10 empty] | •